# Client Project Proposal & Sprint 1 Plan

TEMPLATE & INSTRUCTIONS

# Instructions

This week (either Week 3 or 4), meet with your client and complete Part A — Project Proposal Summary — together with them. This is not a document you write about your client; it's a document you agree with your client. It becomes the shared reference point for what you're building.

Once Part A is agreed and signed off, complete Part B — your Sprint 1 Plan — allocating every task for the first 3 weeks of the Design & Bootstrap sprint across your team. Submit both parts as one document.

Roles on a real client team don't have to match the 5-role structure used in the in-class simulation. Combine or split roles based on what this specific project actually needs (e.g. a BA doubling as a developer, or two people on UX if the project is design-heavy). The only non-negotiable: it must be unambiguous who owns each task – PM,BA and UX tasks are not split, only one person in charge, but a BA can double up as UX.

# Understanding the 3-Sprint Structure

Every capstone project runs the same fixed arc, regardless of what you're building. You'll need to understand this before you can write the roadmap section in Part A. Things may change but overall your definition is always Initiation and Design > Core MVP Feature > Refine MVP  , for short we refer to this as ICR (Initiation, Core , Refined)

If the ICR does not fit your project, you still need to build your project around the three sprints, if this does not fit the client, please invite either Alessio or Nhi into the discussion.

### Sprint 1 — Design & Bootstrap

Two separate tracks run in parallel, not one. Infrastructure is real, not mocked — your web server, database, and storage are actually stood up and live by the end of this sprint. Product is NOT working code — designs and a paper prototype only (a digital mockup, e.g. Figma, is fine — it doesn't need to be literal paper). No working features yet, mocked or otherwise.

This sprint answers: is the plumbing live, and do we know what we're building? Not: does anything work yet.

### Sprint 2 — Core  MVP

The single main feature that proves your project's core value proposition, built end-to-end even if rough. Not polished, not complete — but a real user or client can see the idea works. This sprint answers: does the core idea actually function?

### Sprint 3 — Refine MVP

Hardening, polish, and secondary features if time allows, fixing what Sprint 2 exposed. This sprint answers: is this now presentable and closer to production-credible?

# Part A — Project Proposal Summary

Complete this section during or immediately after your client discussion. (Remove the blue boxes like this one)

## Project Details

Project name: Idea-to-Prototype Acceleration with Agentic LLM Systems

Client / organization: Telstra — muru-D Innovation Lab

Prepared by: 14-Telstra-muru-D — Team 2

Date of client discussion: 07/08/2026 (Alessio Bonti acting as client proxy)

## Team & Roles

List everyone on the team and what they own. Combine roles where the project calls for it — just make sure every task in Part B maps to a name here.

| Role | Assigned to | Notes |
| --- | --- | --- |
| Project Manager | Sean Danailoff | Board, client / supervisor liaison, sign-off. Not assigned any development work. |
| BA / UX | Ziggy Debrincat | Combined role – Requirements and design both owned by one person, per template rules. |
| Developer 1 | Sahil Khan | Front – end and interface implementation. |
| Developer 2 | Senglong Te | Front-end and interface implementation |

## Problem Statement

The muru-D Innovation Lab generates a lot of early stage ideas, but moving from a single sentence concept to something concrete enough to assess is slow and inconsistent. The client’s stated need is a ‘systematic, repeatable AI workflow that takes the lab from a one-sentence idea to a working prototype’. Today that journey depends on individual effort and judgement, so the time and quality of the result may be widely different between different ideas.

## Target Users

Innovation Lab staff at muru-D who assess and progress early stage concepts. This primarily includes the people who test whether an idea is worth pursuing before committing resources to it. Not external Telstra customers, and not the general public.

## Proposed Solution

We propose a proof-of-concept system that decomposes a plain language idea into a structured specification, generates a runnable prototype through a multi-step agentic workflow, and finally measures the quality of what it creates. The measurement layer is central rather than incidental. The client’s requirement is a repeatable workflow, meaning that the output needs to be consistently good, it shouldn’t just create outputs which waste resources (such as tokens). This is a proof of concept and research system, not a production system.

## Scope Boundaries

In scope this term:

- A working end-to-end pipeline: plaintext idea --> Structured specification --> Generated prototype.

- A defined, narrow prototype target (exact scope yet to be confirmed).

- An evaluation framework used to compare models, prompts, and workflow configurations.

- Documentation of the workflow so the lab can repeat and / or extend it.

Out of scope this term:

- Production deployment or Integration with Telstra systems – This is a proof of concept (POC). Integration at Telstra is far beyond a semester of work and would require a security review we cannot complete.

- Handling proprietary, customer or personally identifiable data – Governance constraints are unconfirmed, so we will work only with public example ideas.

- Supporting every prototype type – A narrow, well evaluated target is better than a broad and unmeasured one.

- Cost optimisation at Telstra scale – We will track and report token costs but will not engineer for production scale economics.

## 3-Sprint Roadmap

One sentence per sprint, describing the state of the project at the end of that phase — not a list of activities.

Sprint 1 — Design & Bootstrap: By the end of sprint 1, the servers, database and storage should be running and reachable at a real URL. The team should have a complete design of how the system will work, including a mockup of the interface. Nothing is built yet on either side, this sprint is to prove the plumbing is live and that we all know what we’re making.

Sprint 2 — Raw MVP: By the end of this sprint someone can enter a one sentence idea, and the system should produce a prototype from it, start to finish. It will be incomplete and maybe not the best output, but it will be real enough for the client to see that the core idea is working.

Sprint 3 — Refine MVP: By the end of this sprint, the system is more reliable, and we can show with evidence how well it performs and where it may fall short, the interface will be tidied up. Extra features may be added if time allows.

## Success Criteria

This project is complete when muru-D can take a one sentence idea, run it through the documented workflow and receive a prototype which has evidence showing how reliably it works and where it fails.

Concretely: A demonstrable working pipeline, a written evaluation of the quality of its output, and documentation which allows for the lab to repeat the process without needing our team.

## Assumptions & Constraints

Unconfirmed at time of writing, still requiring client sign-off:

- The project brief has not yet been issues: The brief was being rewritten following discussion between telstra and Alessio Bonti and it was expected by 09/08/26. Therefore, this proposal is based on the 07/08 kickoff discussion and is submitted pending confirmation; scope will likely shift once the brief is received.

- The client has not been directly engaged: Nikhita has been unavailable during this period, with Alessio Bonti acting as proxy. Assumptions here have not yet been validated with the client themselves.

- Governance constraints are undefined: Telstra’s requirements around data handling and model usage were discussed but have not been documented. We have scoped conservatively but are still waiting for guidance.

Constraints the team is working within:

- API access and token budget are unconfirmed: High token costs were raised as a project risk as a poorly designed workflow can consume more tokens for worse results. We assume access to a commercial LLM API but have no confirmed budget.

- LLM non-determinism: Identical prompts can return different outputs, so single run evidence is not reliable. This is why the evaluation framework is in scope rather than optimal.

- Reduced team size: Four members rather than five, so the BA and UX roles are combined.

## Client Agreement

Both the client and a team representative should confirm this proposal reflects what was discussed before Part B is built out.

Client name: Nikhita – Pending availability

Client signature / date: n/a

Team representative: Sean Danailoff (Project Manager)

Team signature / date: Sean Danailoff – 15/08/2026

Part B — Sprint 1 Plan (Weeks 1–3)

Allocate every task for the Design & Bootstrap sprint across your team, week by week. Every task must sit on either the Infrastructure track or the Design/Product track — Sprint 1 has no working features on either track. The tracks are here only to help you separate things with more granularity. 
Remember that every team member needs to contribute 4 solid hours of work per week.

Two example tasks are included below (one per track) to show the level of detail expected. Replace and add cards until every piece of Sprint 1 work is on the board with a clear owner.

## Week 1

Set up Sprint 1 board and task breakdown

| Owner | Sean Danailoff (PM) | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 1 | Hours | 2 |

Description: Create the sprint 1 board, remove the premade template tasks and break the sprint into epics and tasks with owners, weeks and durations.

Deliverable: Sprint 1 board populated and linked to the Master Document

Acceptance criteria:

✓ Premade tasks removed

✓ Epics and tasks created with owner, week and duration.

✓ Board linked to Master Document

Client proposal sign-off and liaison

| Owner | Sean Danailoff (PM) | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 1 | Hours | 2 |

Description: Take the project proposal to the client, confirm scope and assumptions, and obtain sign-off.

Deliverable: Signed proposal, or documented list of items awaiting client confirmation.

Acceptance criteria:

✓ Proposal shared with client

✓ Scope boundaries confirmed or flagged as being open

✓ Outcome recorded in meeting minutes

Draft initial requirements from client discussion

| Owner | Ziggy Debrincat (BA) | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 1 | Hours | 4 |

Description: Turn the client discussion and brief into a requirements document covering the problem, target users and the main feature sprint 2 needs to have completed.

Deliverable: Requirements document committed to the repository and shared with the team.

Acceptance criteria:

✓ Problem and target users documented

✓ Candidate main feature for Sprint 2 identified

✓ Shared with client for confirmation

Research agent orchestration approaches

| Owner | Sahil Khan (Dev 1) | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 1 | Hours | 4 |

Description: Review how existing systems deconstruct an instruction into a plan with multiple steps and then produce a recommendation for the approach this project should take. Research and written recommendation only – no implementation required.

Deliverable: Short recommendation document with options compared and final one proposed.

Acceptance criteria:

✓ At least three approaches compared

✓ Tradeoffs documented (complexity, cost, reliability)

✓ Recommended approach with reasoning

Stand up web server and database

| Owner | Senglong Te (Dev 2) | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 1 | Hours | 4 |

Description: Provision the web server and database the project will run on for the future sprints. Confirm both are reachable, and a placeholder route responds successfully.

Deliverable: Live server and database, confirmed reachable at a real URL.

Acceptance criteria:

✓ Server running successfully

✓ Database created and connected

## Week 2

Board maintenance and task sign-off

| Owner | Sean Danailoff (PM) | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 2 | Hours | 2 |

Description: Keep the board reflecting the reality, verify completion comments, tick off acceptance criteria and move cards as work is completed.

Deliverable: Board accurate at end of week 2

Acceptance criteria:

✓ Every completed card carries a completion comment as well

✓ Checklists ticked only when genuinely complete

✓ No cards sitting in wrong bucket

Meeting minutes and stakeholder communication

| Owner | Sean Danailoff (PM) | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 2 | Hours | 2 |

Description: Chair and minute team meetings, maintain communication with client proxy and supervisor.

Deliverable: Minutes committed to the repository.

Acceptance criteria:

✓ Minutes recorded with attendees, actions and owners

✓ Action items assigned with due dates

✓ Stored in team repository

Map end-to-end workflow

| Owner | Ziggy Debrincat (BA) | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 2 | Hours | 2 |

Description: Document the full process from plaintext idea through specification to a generated prototype, identyfing each stage and what is involved in each stage.

Deliverable: Workflow diagram with written descriptions.

Acceptance criteria:

✓ Every stage from idea to prototype identified

✓ Inputs and outputs defined per stage

✓ Reviewed by both devs.

Wireframe the core screens

| Owner | Ziggy Debrincat (UX) | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 2 | Hours | 2 |

Description: Produce wireframes for the main screens, based on the workflow map. Layout and flow only, no visual design required.

Deliverable: Wireframes shared with the team.

Acceptance criteria:

✓ All core screens covered

✓ Navigation between screens shown

✓ Reviewed by PM and devs.

Scope what counts as a prototype

| Owner | Sahil Khan (Dev 1) | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 2 | Hours | 2 |

Description: Investigate and define what the system will output, a single file page, a multi-file app or an endpoint, document the evaluation of each.

Deliverable: Written scope decision with reasoning.

Acceptance criteria:

✓ Options assessed based on build effort and evaluability

✓ One target recommended

✓ Agreed with the team

Front-end architecture and component plan

| Owner | Sahil Khan (Dev 1) | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 2 | Hours | 2 |

Description: Design the front-end structure, including routes, components and state from the wireframes. Design document only, no implementation required.

Deliverable: Architecture document with component breakdown.

Acceptance criteria:

✓ Component hierarchy documented

✓ Maps clearly to the wireframes.

Configure storage

| Owner | Senglong Te (Dev 2) | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 2 | Hours | 2 |

Description: Configure the storage the project will use for the term.

Deliverable: Storage live and writable from the application environment.

Acceptance criteria:

✓ Access rules configured and deployed

✓ Test write and read confirmed.

Set up CI pipeline and environment configuration

| Owner | Senglong Te (Dev 2) | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 2 | Hours | 2 |

Description: Configure continuous integration to run on every push, document environment variables required to run the project.

Deliverable:

CI running green on the default branch, environment variables documented.

Acceptance criteria:

✓ CI runs automatically on push

✓ Configuration committed to the repository

## Week 3

Risk register and sprint review preparation

| Owner | Sean Danailoff (PM) | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 3 | Hours | 2 |

Description: Record project risks with likelihood, impact and mitigation and prepare the Sprint 1 review for client and supervisor.

Deliverable: Risk register and sprint review pack.

Acceptance criteria:

✓ Risks documented with mitigations and owners

✓ Sprint 1 outcomes summarised against the plan

✓ Reviewed with the team before presentation

Sprint 1 close-out and sign-off

| Owner | Sean Danailoff (PM) | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 3 | Hours | 2 |

Description: Verify every sprint 1 card is complete with evidence, and sign off the sprint.

Deliverable: All sprint 1 cards in Done with completion comments.

Acceptance criteria:

✓ Every card has a completion comment and linked deliverable

✓ Infrastructure confirmed live and reachable

✓ Design prototype confirmed complete

Build clickable digital prototype

| Owner | Ziggy Debrincat (UX) | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 3 | Hours | 4 |

Description:

Turn the wireframes into a clickable digital prototype shower user journey. Design only, no code required.

Deliverable: Clickable prototype shared with the team and client

Acceptance criteria:

✓ All core screens designed to visual fidelity

✓ Journey is clickable end to end

✓ Shared with client for feedback

Draft evaluation criteria

| Owner | Sahil Khan (Dev 1) | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 3 | Hours | 2 |

Description:

Define concretely what makes a generated prototype ‘good’, the scoring will be used in sprint 3.

Deliverable: Written evaluation criteria agreed by the team.

Acceptance criteria:

✓ Measurable criteria defined

✓ Scoring approach documented

✓ Agreed with team and recorded in the repository

Set up design system and UI kit

| Owner | Sahil Khan (Dev 1) | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 3 | Hours | 2 |

Description:

Establish colours, typography, and base styles in the repository from the prototype.

Deliverable: Design tokens and base styles committed.

Acceptance criteria:

✓ Colours and typography defined in code

✓ Base component styles created

✓ Matches the digital prototype

Document deployment and provide team access

| Owner | Senglong Te (Dev 2) | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 3 | Hours | 2 |

Description:

Write up how the environment is deployed and configured and ensure every team member can access and run it.

Deliverable: Deployment documentation in the repository.

Acceptance criteria:

✓ Deployment steps documented

✓ Every team member has access and has run it successfully

Verify infrastructure end to end

| Owner | Senglong Te (Dev 2) | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 3 | Hours | 2 |

Description:

Confirm server, database and storage are all live and reachable, closing out the infrastructure track for sprint 1.

Deliverable: Verification record confirming all components are live.

Acceptance criteria:

✓ Server can be reached at a real URL

✓ Database read and write confirmed

✓ Storage read and write confirmed

Totals: Week 1 = 16hrs, Week 2 = 16hrs, Week 3 = 16 hrs. 48 hours, 12 per person, over 3 weeks.